## Project Overview
PARQ Integration Stakeholder Dashboard
Readable without opening markdown files
Dashboard purpose | Stakeholder-friendly view of PARQ Integration status, deliverables, questions, risks, and dependencies.
Audience | Product Team, Business Team, Vendor Team, Management
Source basis | Repository files only. No new requirements were created.
Recommended tabs | Project Overview; Deliverables Tracker; Open Questions Tracker; Risk Register; Dependency Tracker
Latest repository date observed | 2026-06-11
Key current decision | BMS Option B: login-time BMS check is non-blocking; app entry continues if BMS is unavailable.
Primary open management item | Named owners and environment readiness remain unconfirmed for several vendor/system dependencies.
Metric | Value | Notes
Tracked deliverables | 12 | From MASTER_INDEX.md
Open questions | 12 | From clarification log and technical control pack
Open risks | 15 | From technical dependency control pack
Tracked dependencies | 12 | Vendor/system dependencies
Missing source artifacts | 1 | Proposal PDF unavailable
Recommended Tab | Purpose | Main Users
Project Overview | Executive summary and dashboard key points | Management, all teams
Deliverables Tracker | Artifact inventory, owner, status, source path, downstream consumer | Product, PM, Management
Open Questions Tracker | Decision and information gaps requiring owner response | Business, Product, Vendor
Risk Register | High-level project risks and mitigation needs | Management, PM, Vendor
Dependency Tracker | System/vendor dependency visibility and readiness gaps | Vendor, QA, Architecture

## Deliverables Tracker
Deliverables Tracker
Stakeholder-readable tracker generated from repository source files
ID | Deliverable | Category | Owner | Status | Source / Input File | Downstream Consumer | Notes
PARQ-SOT-001 | PARQ Phase 1 User Flow Index | Source of Truth | TBD | Current | 01_Source_of_Truth/PARQ_User_Flow/The_PARQ_Phase_1_User_Flow_Index.xlsx | 03_Architecture, QA, Product | Primary feature/user-flow source.
PARQ-SOT-002 | PARQ Clarification Decision Log | Source / Decision Log | Libra | BMS decision recorded / open questions | 01_Source_of_Truth/Clarifications/PARQ_Clarification_Decision_Log.md | All agents | BMS Option B recorded; proposal and owner gaps remain open.
PARQ-ARCH-001 | PARQ User Flow Integration Architecture | Architecture | TBD | Current | 03_Architecture/PARQ_User_Flow_Integration_Architecture.md | Simon, Quinn, Molly, PARQ | Maps flows, dependencies, failure cases, and sequence candidates.
PARQ-ARCH-004 | PARQ Data/API/Boundary/Vendor Matrix | Architecture | TBD | Current | 03_Architecture/PARQ_Data_API_Context_Boundary_Vendor_Matrix.md | Simon, Quinn, PARQ | Data ownership, API inventory, context, and vendor dependencies.
PARQ-ARCH-005 | PARQ Technical Dependency Control Pack | Architecture / Control | Simon | Draft / Open Questions | 03_Architecture/PARQ_Technical_Dependency_Control_Pack.md | Quinn, PARQ, Libra | Vendor/API ownership, PII, error baseline, readiness inputs.
PARQ-ARCH-006 | PARQ Visual Architecture and Flow Pack | Architecture / Visual | Simon | Draft / Open Questions | 03_Architecture/PARQ_Visual_Architecture_and_Flow_Pack.md | Business, vendor, management, Quinn | Visual context, boundaries, dependencies, sequences, risks.
PARQ-ARCH-007 | PARQ BMS Identity Flow Impact Assessment | Architecture / Decision Impact | Simon | Draft / Option B Non-Blocking Decision Recorded | 03_Architecture/PARQ_BMS_Identity_Flow_Impact_Assessment.md | PARQ, Molly, Quinn, Libra | BMS login behavior decision recorded; technical controls remain open.
PARQ-UX-001 | PARQ UX Stakeholder User Flow Pack | Discovery / UX | Molly | Draft / Open Questions | 02_Discovery/PARQ_UX_Stakeholder_User_Flow_Pack.md | UX/UI, business, stakeholders | Journey-first stakeholder flow artifact.
PARQ-REVIEW-001 | PARQ Integration Architecture Review | Discovery / Review | TBD | Reference | 02_Discovery/PARQ_Integration_Architecture_Review.md | Simon, Libra | Historical-only vs active reference still unconfirmed.
PARQ-SYS-002 | BMS Member API Reference | Source Reference | TBD | Current | 01_Source_of_Truth/API_and_System_References/00_2025_Document/api-members-by-account-id.md | Simon, Quinn | BMS GET /members/by-account-id source reference.
PARQ-SYS-003 | Add Identity Flow with BMS CheckMember | Source Reference | TBD | Current | 01_Source_of_Truth/API_and_System_References/00_2025_Document/add_identity_flow.md | Simon, Quinn, Molly | Confirms current BMS usage in identity flow.
PARQ-MISSING-001 | Proposal: The PARQ integration.pdf | Missing Source | TBD | Unavailable | Not found in repository | Libra, Simon, PARQ | Must be uploaded/linked or formally accepted as unavailable.

## Open Questions Tracker
Open Questions Tracker
Stakeholder-readable tracker generated from repository source files
ID | Open Question | Owner | Status | Source / Input File | Downstream Consumer | Theme
OQ-CLAR-001 | Where is [Proposal] The PARQ integration.pdf, or who can provide the approved source file/link? | TBD | Open | MASTER_INDEX.md; PARQ_Clarification_Decision_Log.md | Libra, PARQ, Simon | Source traceability
OQ-CLAR-002 | Is there an approved clarification note or decision record behind older architecture references? | TBD | Open | PARQ_Clarification_Decision_Log.md | All agents | Source traceability
OQ-CLAR-004 | Is PARQ_Integration_Architecture_Review.md historical-only or still an active reference? | TBD | Open | MASTER_INDEX.md | Libra, PARQ, Simon | Document governance
OQ-BMS-001 | What is the exact technical endpoint and payload contract for login-time BMS member check? | IAM/BMS owners TBD | Open | PARQ_Clarification_Decision_Log.md; PARQ_BMS_Identity_Flow_Impact_Assessment.md | Simon, Quinn | BMS Option B
OQ-BMS-002 | What timeout, retry, circuit-breaker, audit, and monitoring behavior applies to non-blocking BMS login refresh? | IAM/BMS owners TBD | Open | Technical Dependency Control Pack | Simon, Quinn, PARQ | BMS Option B
OQ-BMS-003 | If BMS returns member-bound-to-another-account during login, what support message and correction path apply? | PARQ/IAM/Support TBD | Open | Clarification Decision Log | Molly, Quinn, Simon | Support flow
OQ-BMS-004 | What cache/source detects previous Workplace permission while BMS is unavailable, and what freshness limit applies? | IAM/FS owners TBD | Open | Clarification Decision Log; Technical Dependency Control Pack | Simon, Quinn | Fallback behavior
OQ-OWN-001 | Who are the named owners for each indexed folder and document? | Project leads | Open | MASTER_INDEX.md | Libra, PARQ | Ownership
OQ-API-001 | Who owns SSO, IAM, FS, BZB, Argento, CMS, Kafka/Event Bus, BMS, Notification, Elevator, Turnstile APIs? | PARQ / system owners | Open | Technical Dependency Control Pack | Simon, Quinn, PARQ | Dependency ownership
OQ-PII-001 | What are field-level PII, consent, retention, and deletion rules per system/API? | Security/privacy owner TBD | Open | Technical Dependency Control Pack | Simon, Quinn, Management | Compliance
OQ-ENV-001 | What SIT/UAT/PVT endpoints, credentials, data sets, hardware paths, and readiness dates are available? | PARQ / Quinn / vendors | Open | Technical Dependency Control Pack | Quinn, PARQ, Vendor team | Environment readiness
OQ-PAY-001 | What idempotency, reconciliation schedule, refund flow, and support path apply to Argento/FS/OBK parking payment? | OBK Backend / Argento / FS TBD | Open | Technical Dependency Control Pack | Simon, Quinn, Vendor team | Payments

## Risk Register
Risk Register
Stakeholder-readable tracker generated from repository source files
ID | Risk | Severity | Impact | Mitigation / Required Decision | Owner | Status
R-001 | Named owners for external APIs are not confirmed. | High | Dependency follow-up and defect triage may stall. | Confirm named owner for each system/API. | PARQ / project leads | Open
R-002 | Proposal PDF is missing from repository. | Medium | Source traceability gap for proposal-derived assumptions. | Upload/link approved proposal or accept existing review as sufficient reference. | PARQ / Libra | Open
R-003 | Clarification source is incomplete as standalone artifact. | Medium | Architecture may rely on clarification content that is not independently traceable. | Add approved clarification source or decision entries. | PARQ / Libra / Simon | Open
R-004 | PII field-level mapping is incomplete. | High | PDPA, consent, deletion, and vendor sharing risks remain uncontrolled. | Create approved PII/consent field matrix per API/system. | Security/privacy owner TBD | Open
R-005 | BZB conflict and wrong-merge correction process is not operationally defined. | High | Account merge errors may require ad hoc backend fixes. | Define correction runbook, approval, and audit trail. | IAM/BZB/support owners TBD | Open
R-006 | FS is a multi-service dependency without per-service SLA/error contract. | High | Parking, visitor, elevator, turnstile, workplace, and traffic may fail inconsistently. | Split FS API ownership and define SLA, timeout, retry, error catalog per service. | FS owner TBD | Open
R-007 | QR single-use/replay behavior is not confirmed. | Medium | Access control may be weaker or inconsistent for visitors. | Decide reusable-window versus single-use policy. | FS / security / access owner TBD | Open
R-008 | FS outage behavior for turnstile/elevator is undefined. | High | Physical access may fail during network/system outage. | Define online validation outage policy and site fallback. | FS / site operations TBD | Open
R-009 | Argento/FS/OBK payment reconciliation details are incomplete. | High | Paid-but-unsynced parking tickets and refund disputes may occur. | Define idempotency, reconciliation, refund, and support escalation. | OBK Backend / Argento / FS TBD | Open
R-010 | CMS Phase 1 seed account may expose broader OBK data. | High | Data isolation and operational access risk. | Decide compensating control or risk acceptance. | CMS / security / PARQ TBD | Open
R-011 | Notification segment ownership and cleanup verification are not defined. | Medium | Wrong audience or stale data after deletion. | Assign segment owner and cleanup validation. | Notification / IAM TBD | Open
R-012 | Kafka/Event Bus retry and dead-letter behavior is unknown. | Medium | Permanent-delete cleanup may silently fail. | Confirm topic schema, consumers, retry, DLQ, replay. | Event platform TBD | Open
R-013 | SIT/UAT/PVT readiness lacks endpoint, data, and hardware dates. | High | Quinn cannot finalize planning or dependency gating. | Provide environment readiness tracker with owners and dates. | PARQ / Quinn / vendors | Open
R-014 | Phase 1.5 OCR/rate config dependencies may cause rework if deferred too far. | Medium | Parking e-stamp and fee calculation may need retrofit. | Reserve Phase 1.5 data model and ownership decisions early. | PARQ / Simon / FS / CMS / TCCT TBD | Open
R-015 | BMS non-blocking login refresh has unresolved controls. | High | Users may enter app but see stale/missing Workplace persona or require unclear support path. | Define endpoint/payload, timeout, circuit-breaker, cache/source, support, PII, audit. | IAM / BMS / PARQ / support TBD | Open

## Dependency Tracker
Dependency Tracker
Stakeholder-readable tracker generated from repository source files
System / Vendor | Role | Criticality | Owner | Interfaces / Data | Impact if Unready | Open Items
SSO | Authentication and identity orchestration | High | TBD | POST /user/exists; POST /oauth/token; conflict behavior | Users cannot login/register if unavailable. | Owner, token/error contract, environment readiness
IAM | Local member profile and persona entitlement | High | TBD | GET /identity/validate; POST /auth/login; Account Merge; BMS orchestration | Persona and account lifecycle become unreliable. | Profile overwrite policy, deletion orchestration, BMS mutation rules
BMS | Member lookup, non-blocking login refresh, cleanup consumer | Medium/High | TBD | GET /members/by-account-id; checkMember; deletion cleanup | Persona freshness may degrade; cleanup/compliance risk. | Endpoint/payload, timeout, previous-permission source, audit, PII
FS / Iviva | Workplace, parking, visitor, elevator, turnstile, traffic authority | High | TBD | Entitlements, floors, parking, visitor, QR validation, hardware | Access, parking, visitor, elevator, turnstile can fail. | Split service owners, SLAs, error catalog, hardware readiness
BZB / Buzzee Bee | Retail identity and privilege source | High for merge | TBD | Email/phone lookup, BZB member ID, linkage sync | Retail persona merge may fail or mislink. | Duplicate handling, wrong-merge correction, deferrable behavior
Argento | Payment gateway and refund execution | High for parking payment | TBD | PromptPay initiation, callback, refund | Parking payment unavailable or unsynced. | Callback security, idempotency, reconciliation, refund process
CMS | Admin visibility and operational tooling | Medium / Phase 1.5 High | TBD | User view, visitor visibility, notification audience, car park config | Operational support and data isolation gaps. | Seed admin scope, RBAC/org filtering, compensating controls
Kafka / Event Bus | Async cleanup/event distribution | Compliance-critical | TBD | ob-iam.account.permanent-deleted | Hard-delete cleanup may fail silently. | Schema, producer/consumer SLA, retry, DLQ, replay
Notification Infrastructure | PARQ targeting and device/inbox cleanup | Medium | TBD | Segments, device tokens, inbox records | Wrong audience or stale tokens after delete. | Segment owner, token cleanup, validation
Elevator System | Physical access hardware | High | TBD | Elevator command/status through FS | Authorized access may fail at site. | Hardware test environment, floor mapping, timeout/fallback
Turnstile System | Physical access hardware | High | TBD | QR scan and online FS validation | Access may be denied/allowed incorrectly. | Outage policy, latency threshold, audit retention
TCCT OCR | Phase 1.5 ticket recognition | Deferred / High later | TBD | OCR endpoint, ticket image/token, confidence | Automated e-stamp cannot launch. | API owner, sample data, image retention, confidence thresholds